## Sheet1
Activity Task | Activity Phase | Audience | Start Date | Date Due | Responsibility | Status | Notes
Get permission to capture Drone Footage at Minnona Terrace | Pre | N/A | 2016-11-21 | 2016-11-25 | Brad, MT | Completed | Drone Contract too extensive with Requirements. Switching to FaceBook Live type Posts. | Status Legend
Capture FaceBook Live as well as other video footage of Minnona Terrace that can be used in Marketing/Communication pieces | Pre | N/A | 2026-11-25 | 2016-12-02 | Brad, MT | Started | Switch from Drone Footage will begin Video Capture on week of 11/28 | Not Started
Establish the ability to post Facebook Live segments to the District 35 Website, Facebook Page, Twitter Account | Pre | N/A | 2016-11-21 | 2016-12-02 | Brad,Barbara Wiesenberger and Christine Piela | Completed | Have the approach understood for the Webpage from Barb. Have approach from Christine on District FB and Twitter. | Started/Ontrack
Create canned PR Pieces to send to each club VP PR | Pre | VP PRs | 2016-11-21 | 2016-12-05 | Christine Piela, Brad Laatsch | Started | Awaiting Response from Christine | Delayed
Confirm ability to do email blast and Newsletter to D35 Officer Base and General Membership | Pre | N/A | 2016-11-21 | 2016-12-02 | Brad Laatsch, Kelly Huttelmaier | Completed | Confirmed no techincal limitations or frequency limitations. | Completed
Develop “TM Brad for D35 TV” Persona and logo | Pre | N/A | 2016-11-20 | 2016-11-20 | Brad Laatsch | Completed
Have speakers record 2-3, 30 second spot that can be used in monthly outreach one for officers and one general member base. | Pre | Club Officers, General Member Base | 2016-11-28 | 2016-12-05 | Brad, Speakers | Not Started | Continue Task as new speakers are identified
Involve Trio in FaceBook Live Posts during club visits | Pre | Club Officers | 2016-12-01 | 2017-01-27 | Trio | Not Started | Ongoing as
Create a give away. Club Board Promo video, about what the board is looking forward to for the TLI. Top video to be selected by trio. Reward is all officers in the club chosen will receive free attendance and meal for officers in attendance, Individual session with Mark Brown . Winning Board to be chosen 1st week of January. | Pre | Club Boards | 2016-12-09 | 2016-12-15 | Brad, Keith | Not Started | Tie into first Newsletter article
Ask Rory Vaden 10-15 sec promo on TLI highlighting Mark Brown | Pre | Club Officers, General Member Base | 2016-12-01 | 2016-12-09 | Brad Rory Vaden | Not Started | FaceBook Posting
Prizes for people that comment on FaceBook Live Posts. "Be the first person to comment and win a TM prize each week on FaceBook Live post". Winners must be in attendance to get prize. | Pre | Club Officers, General Member Base | 2016-11-28 | 2016-12-02 | Brad, Keith | Not Started | Link to social Media postings. $100 Budget for Prizes
Establish possibility of calling into each Division’s Council Meeting (To be performed by District Trio and Members of Trio Planning committee) | Pre | District Councils | 2016-12-01 | 2017-01-27 | District Trio, TLI Comitttee | Not Started | Conduct as aligned to District Council(s) Dates
Develop Slides for DEC and TRIO Calls | Pre | DEC, TRIO | 2016-12-12 | 2016-02-04 | Brad | Not Started | Have ready for 1st DEC on 12/17
Confirm “Green Room” Space for TM Brad Interviews | Pre |  | 2016-11-21 | 2016-12-02 | Brad, TLI Committee | Not Started
Launch first weekly Social Media Pieces (FaceBook, Website and Twitter Account) | Pre | Club Officers and General Member Base | 2016-12-05 | 2017-02-02 | Brad, District SoME Team | Not Started
Launch first monthly email blast | Pre | Club Officers | 2016-12-15 | 2016-12-25 | Kelly Huttelmaier, Brad | Not Started | 1st only to Club Officers tie to Newsletter going live for December
Write December newsletter article for D35 newsletter include link to TM Brad Video Segments | Pre | General Membership Base | 2016-12-12 | 2016-12-15 | Brad | Not Started
Link to EventBrite | Pre | General Membership Base | 2016-12-03 | 2016-12-15 | Theresa, Brad | Not Started | Provide TLI Communication info to Theresa for inclusion on Eventbrite
Present at DEC | Pre | DEC | 2016-12-17 | 2016-12-17 | Brad | Not Started
Present on TRIO Call | Pre | TRIO | TBD | TBD | Brad | Not Started | Ask Keith
Continue weekly Social Media Pieces (FaceBook, Website and Twitter Account) | Pre | Club Officers and General Member Base | 2017-01-02 | 2016-01-27 | Brad | Not Started
Continue Monthly email blast | Pre | Club Officers and General Member Base | 2017-01-15 | 2017-01-25 | Kelly Huttelmaier, Brad | Not Started | Includes alll Members tie to Newsletter Release
Write January newsletter article for D35 newsletter include link to TM Brad Video Segments | Pre | Club Officers and General Member Base | 2017-01-11 | 2017-01-15 | Brad | Not Started
Link to EventBrite |  | General Member Base | 2017-01-12 | 2017-01-15 | Theresa, Brad | Not Started | Provide TLI Communication info to Theresa for inclusion on Eventbrite
Present at DEC | Pre | DEC | 2017-01-21 | 2017-01-21 | Brad | Not Started
Present on TRIO Call | Pre | TRIO | TBD | TBD | Brad | Not Started | Ask Keith
Final weekly Social Media Pieces (FaceBook, Website and Twitter Account). | Pre | Club Officers and General Member Base | 2017-01-27 | 2017-01-27 | Brad | Not Started
FaceBook Live Segments with the TM Brad in the “GreenRoom”. | At Event | Speakers and TLI Attendees | 2017-02-04 | 2017-02-04 | Brad | Not Started
Record Video Thank You with the Trio to be sent/posted the week of 2/6 | At Event | Club Officers and General Member Base | 2017-02-04 | 2017-02-04 | Brad, Trio | Not Started
Record Video Thank You from each speaker to be sent/posted the week of 2/6 | At Event | Club Officers and General Member Base | 2017-02-04 | 2017-02-04 | Brad, Speakers | Not Started
Post/Send Video Thank You with the Trio to be sent/posted the week of 2/6 | Post Event | Club Officers and General Member Base | 2017-02-06 | 2017-02-25 | Brad, SoME Team | Not Started | Date Range Includes SoMe and Newsletter timelines
Post/Send Video Thank You from each speaker to be sent/posted the week of 2/6 | Post Event | Club Officers and General Member Base | 2017-02-06 | 2017-02-25 | Brad, SoME Team | Not Started | Date Range Includes SoMe and Newsletter timelines
After Action Review | Post Event | Trio and TLI Committee | TBD | TBD | TLI Committee | Not Started
Note on E10: Bradley Laatsch: Check Newsletter due date