## Tasks
Category (support sorting) | Task | Date Range Due (est. start prior to..) | Status | Responsible for (can adjust or delegate) | Name(s) | Comments (Note this is not an inclusive task list, but can be used in conjunction with other sources)
1GP | General Planning (GP) | 5 mos.
1GP | Convention Chair selected | 5 mos. | Done | PQD |  | Haley Loprieno, Shamaine Schoenherr
1GP | Room setups (see the Setup tab on this spreadsheet) | 2 mos. |  | PQD |  | Initial general set up done on Contract. Work with Hotel contact person on detail room changes 1-2 months before conf. Review with Top 3 and Conf. Chair
1GP | Public Relations Blitz | 3 mos. |  | PRC, CC |  | To Toastmasters; and local area as appropriate.
1GP | Review District 35 Procedure Manual on Conferences | 3 mos. |  | TRIO |  | Look for Convention related items
1GP | Review District Administrative Handbook for convention info. | 3-4 mos. |  | TRIO |  | Look for Convention related items
1GP | Review D35 Conference Manual | 4 mos. |  | TRIO |  | Manual Provided by PQD from Mike Zelm includes several attachments
1GP | Provide for display tables (Publicity, Speech craft, etc.) | 2 mos. |  | PQD |  | Part of detail room set up
1GP | First timer activities | 3 mos. |  | PQD, CC |  | Part of hotel set up of rooms. Arrange for ribbons, drinks, food.
1GP | PDG/PDD Dinner - Room reserved | 3 mos. |  | PQD |  | Notify PDD of what room
1GP | Committee Chairs selected | 4 mos. |  | CC |  | All but facilities a/o 9-June
1GP | Committee Chair meetings | 4 mos. |  | CC, ComC
1GP | District Conv walk throughs | 3, 2, 1, mos. |  | TRIO+1 |  | May or may not be need planning walk thru sessions. 15-Oct confirmed
1GP | DEC meeting updates | 3, 2, 1, mos. |  | CC |  | May want at each of the 2-3 prior months of a convention
1GP | Contract Reviewed 3 mo. Prior | 3 mos. |  | PQD, CC
1GP | Select meals by Top 3 | 3 mos. |  | TRIO |  | Top 3 should discuss to choose. Try to stay with 2 selections as usually $1 added for each entrée after one.
1GP | Notify hotel - meal selections, coffee Saturday morning, Snacks Friday night | 2-3 mos. |  | PQD |  | Work with hotel staff to adjust any menu items from standard if cost issue. Confirm initial counts. Provide final room layouts, AV needs (e.g. Microphones)
1GP | Host Club identified | 3 mos. |  | PQD |  | Have banner with stand if possible.
1GP | Photographer | 1 mo. |  | PQD |  | Select and notify.
1GP | Opening Ceremonies Dignitary | 2 mos. |  | CC |  | Welcome to city. Get help from locals and District
1GP | Opening Ceremonies Color Guard | 2 mos. |  | CC |  | VFW or Boy Scouts
1GP | Locate Communication and Leadership Recipient (optional) | 2 mos. |  | PQD |  | Optional as may decide on other keynote speaker, or not have one
1GP | Notify head table of formal wear | 2 mos. |  | PQD |  | Usually applies only to Spring
1GP | Head Table name tags | 2 wks |  | District Master Host
1GP | Determine Spring Dist. Off. Induction process | 1-2 mos. |  | PQD
1GP | Parade of banners | 2 wks |  | District Master Host |  | Prepare lists and get help to organize
1GP | Publish Council Mtg. Agenda | 1 mo. |  | PQD |  | 1-2 months before event
1GP | Meet to select award winners | 1 - 2 mos. |  | TRIO+1 |  | After submit deadline, meet to select top bulletins, web sites, TM of the Year, AG of the Year, Div. Gov. of the Year, Governors Club
1GP | Room Setup Verified | Day of |  | FC |  | Work with hotel staff to make sure room is properly set. Could have a Facilities Chair (PPQD?)to verify set up
1GP | Signs - Educ. Sessions, etc. | 2 wks |  | FC |  | Identify what hotel will do, then provide rest needed.
1GP | Sound systems | 1-2 mos. |  | FC |  | Confirm Harvey Hoernke's availability
1GP | Website updates | 3, 2, 1, mos. |  | PQD, Web Master
1GP | Business Meeting Agenda | 5 wks |  | DD |  | Email to District Council, plus may need help to distribute (?) prior to meeting.
2AW | Awards | 4 mos.
2AW | Awards & Plaques identified | 3 mos. |  | PQD |  | See District Procedure Manual, plus what PQD chooses
2AW | First timer ribbons | 2 mos. |  | PQD |  | PQD order, and get to Reg. Chair
2AW | Provide Bulletin, Web site contests, Toastmaster of the Year applications | 3 mos. |  | PQD |  | E-blast, D35 Web Site announce including rules and forms
2AW | Awards & Plaques ordered | 3 mos. |  | PQD |  | Determine what lettering done at TI, and what might be done locally.
2AW | Hall of Fame | 2, 1 mos. |  | PQD, Hall of Fame staff |  | Coordinate providing information in the spring to the Hall of Fame staff
2AW | Awards & Plaque engraved | 1 mo. |  | PQD |  | Complete any engraving when trophies arrive that is not done by TI
3FIN | Financial: | 3-4 mos. |  | FM |  | Base off District Budget
3FIN | Budget | 3 mos. |  | FM |  | Based off District Budget. Need meal costs and PQD may have other specific costs. See Conference Book.
3FIN | Budget review | 3 mos. |  | TRIO, CC
3FIN | Approve any expenditures | 3, 2, 1 mo. |  | PQD, CC |  | Could set a limit for no approval or provide list of authorized items
3FIN | Conv. Audit | 2 mos. |  | Audit Comm, FM |  | Determine audit support needs. Do audit post convention within 1-2 months.
3FIN | Registration fees to Financial Chair | 3, 2, 1 mo. |  | FM, REG |  | Periodically deposit reg. fees. Maintain audit documentation.
3FIN | Financial - Deposit Reg. Fees | 3, 3, 1 mo. |  | FM
4CT | Contest: | 4 mos.
4CT | Contest Equipment | 1 mo. |  | PQD |  | Make sure we have timing lights and stop watches for the contest.
4CT | Contest Forms | 2 mo. |  | PQD |  | Get from TI for Chief Judge
4CT | Contest Master, Chief Judge | 1 mo. |  | PQD |  | Assign Contest Master, Chief Judge. Inform Contest Master on how much you want them to do.
4CT | Certificates Participation Appreciation | 3 mos. |  | PQD |  | Order Certificates. See Awards for contest trophies
4CT | Identify Contestants | 1 mo. |  | PQD |  | Find out winners of division contests, and runner up
4CT | Friday Night Contest | 4 mos. |  | PQD |  | Determine if have. If, include in planning contests
4CT | Contest Chair | 1 mo. |  | PQD |  | Assign Contest Chair
5CRE | Credentials: | 4 mos.
5CRE | Credentials desk placement | 2 mos. |  | FC |  | Part of detail room set up
5CRE | Credentials Ballots/Lists | 1 mo. |  | CRED |  | Create, bring list of officers, ballots and collection baskets
5CRE | Credentials desk staffing | 1 mo. |  | CRED |  | Assigned by PQD
6ED | Education Sessions: | 4 mos.
6ED | Education Sessions arranged | 3, 2 mos. |  | PC |  | Possibly 3 months prior ask for presenters and identify topics
6ED | Educ. Session Equipment Needs | 1 mo. |  | PC |  | Make sure all of the presenter have the equipment they need in order to present. At least one month prior.
6ED | Evaluation forms distribution | Day of |  | PC
6ED | Education Session handouts | 1 mo. |  | Presenters |  | Each presenter will be responsible for their own handouts. Ask if District pays for.
6ED | Evaluation forms | 1 mo. |  | PC |  | Prepares and prints
6ED | Certificates of Appreciation | 3 mos. |  | PC |  | Order with awards
7FN | Friday Fun Night | 3 mos. |  | Friday Night Chair
7FN | Door Prize solicitation | 1 mo. |  | Friday Night Chair
7FN | Determine Fun event | 2-3 mos. |  | Friday Night Chair |  | Could plan for anytime Friday Fun night chair identified.
7FN | Friday Speak-a-thon | 2 mos. |  | PQD, Hosting Club |  | Assign Club to Coordinate
8HOS | Hospitality room | 2-3 mos. |  | PQD |  | As hotel allows, coordinate who will handle this. Could include PQD arranging use of a conference room.
9ID | International Director if still apply | 4 mos.
9ID | International Director Candidate Table | 3 mos. |  | PQD, CGD |  | Part of detail room set up
9ID | International Director Liaison | 2 mos. |  | CGD |  | Work with the ID to arrange pick up and drop off at the airport and to provide transportation while they are here
9ID | International Director Visits | 2 mos. |  | CGD |  | Arrange for the visiting International Director to visit local businesses to encourage them to start Toastmaster clubs.
9ID | Arrange for Conv. Registration | 2 mos. |  | CGD |  | Make sure ID completes a registration form
9ID | Arrange for hotel accommodation | 2 mos. |  | CGD |  | Determine if comp room or an upgraded room is appropriate and make the hotel guest room request.
10GS | Guest Speaker: | 4 mos. |  |  |  | If any are invited (special speakers, C & L Recipient, etc.)
10GS | Guest of District | 3 mos. |  | PQD |  | Invite and determine any protocol
10GS | Guest transportation if being provided | 2 wks |  | PQD |  | Work with the guest to arrange to pick up and drop off at the airport and to provide transportation while they are in town -- if required.
10GS | Arrange for Conv. Registration of Guest | 1 mo. |  | PQD |  | Make sure District Guest completes a registration form
10GS | Arrange Guest hotel accommodation if being provided | 1 - 2 mo. |  | PQD |  | Determine if comp room or an upgraded room is appropriate and make the hotel guest room request.
11PRG | Programs: | 4 mos.
11PRG | Programs - Composite Conf | 2,1 mo |  | ProgC |  | Create and print composite program for entire event; could have separate ones for Opening Ceremonies, Lunch, Dinner also. All information for composite due 24 days prior to convention
11PRG | Programs - get approval by PQD | 1 mo. |  | ProgC
11PRG | Program Speech Contest | 2 wks |  | ProgC |  | Create and print program - should not combine with composite program
11PRG | Program Opening Ceremonies, Lunch, Dinner (optional) | 3 wks |  | ProgC |  | Create and print program, if have
11PRG | Program - get final count to print | 1 mo. |  | ProgC |  | Provide to Program Chair count for each program
11PRG | Programs - give printed composite to Reg. Chair | 3 wks |  | ProgC |  | For registration table
12PPQD | PDG/PDD Dinner | 3 mos. |  | PDG assigned |  | Work with Second Immediate Past District Governor to make arrangements for the PPQD dinner.
13RG | Registration: | 4 mos. |  | REG
13RG | Get Reg. Spreadsheet sample from prior Reg. Chair or … | 3 mos. |  | REG |  | Also read Registration section in the D35 Conference Guide manual
13RG | Report on attendance and meal counts (post initial planning) | 2 mos. and ongoing |  | REG, PQD |  | Initially use counts for prior couple conferences and PQD to estimate attendance for name tags, meals, etc., then track registrations
13RG | Verify budget available | 2 mos. |  | REG, CC |  | For envelopes, candy?, copies,
13RG | Contact Chamber of Commerce | 2 mos. |  | REG |  | Contact Chamber of Commerce to see what they provide. Sometimes name badges and handouts
13RG | Goodie Bag & Contents | 2 mos. |  | REG |  | Could assign to a committee chair. Could contact Chamber of Commerce for list of local businesses that donate for conferences
13RG | Goodie bag assemblage | 2 wks |  | REG |  | Get helpers or delegate to a committee chair
13RG | Meal Tickets | 3 mos. |  | REG |  | Make up color coded tickets. Track count while processing applications.
13RG | Name Badges | 2 mos. and ongoing |  | REG |  | Check with Chamber of Commerce for what they provide, check with PQD on what D35 can provide (first timer ribbons, name tag plastic holders and lanyards)
13RG | Notify Hotel of initial meal count | 3 mos. |  | PQD |  | Do this when arrange meals with hotel
13RG | Notify Hotel of meal count changes | 2 wks, 1 wk. 3 days, |  | PQD, CC |  | Hotels want firm count 72 hours before start of event - so Monday prior. Hotels are ok if want minor changes up to event start. But can always discuss with them.
13RG | Verify with PQD meal tickets for last 4 days plus at conf. | 1 wk. |  | PQD, CC |  | After final count given to hotel, still get some walk-ins and mail last couple days (but not many) so pad final count
13RG | Protocol List provided | 3 mos. |  | PQD |  | Registration Chair get from PQD for when forms submitted
13RG | Registration desk procedures | 1 mo. |  | REG |  | Determine set up, volunteers, forms, etc.
13RG | Prepare cash box | 1 wk. |  | REG |  | Get seed money from District Finance Manager
13RG | Registration desk staffing | 1 mo. |  | REG |  | Could start lining up at officer training
13RG | Registration - receive Registration and process | 3, 2, 1 mo. |  | REG |  | Maintain spreadsheet of all registrations - paid and protocol. Track any reimbursements which are done thru District Finance Manager
13RG | Registration Form Create | 3 mos. |  | PQD |  | Create and post to the website
13RG | Coordinate get main program | 2 mos. |  | REG, PC |  | Need to have at Registration Desk to hand out
13RG | Registration Form Reg. Desk | 1 wk. |  | REG |  | Print 20 copies for walk-ins(10 for contest only), and 8 club reg. forms. May need separate tracking form for walk in registrations
13RG | Registered Dignitaries Tracked | 3, 2, 1 mo. |  | REG |  | Could be PDG/PDD, PIDs, IDs to give to PQD
14HS | Hotel Selection | 17 mos.
14HS | Select hotel for conference | 17 mos. |  | Site Selection/PQD |  | See detailed task list. Includes general room needs
Note: District officers will be doing other standard tasks that convention committee need not know about, so not everything listed.
Note: This is not an inclusive list, especially since a PQD may choose to do something that is different than prior PQD.
Note: The organization and committees could vary.
Note: See Conference Book for general information, and more details on some of the tasks.
Note: Program Quality Director needs to approve all major decisions, especially if money involved.
DD | District Director
PQD | Program Quality Director
CGD | Club Growth Director
CC | Club Growth Director
REG | Registration Chair
PC | Program Chair
PDG | Past District Governor(s)
PDD | Past District Director(s)
TRIO | DD, PQD, CGD
TRIO+1 | Trio and IPDD
PRC | Public Relations Chair
ComC | Committee Chairs
CRED | Credentials Chair
FC | Facilities Chair
ProgC | Programs Chair
FM | Finance Manager

## Setup
Friday |  | Time | Setup | Layout
Registration Area | Lobby | 03:00 PM thru 08:30 PM | Three 6ft tables, 4 chairs |  | Note this is a sample start and
Friday Fun Night | Room? | 07:00 PM thru 10:00 PM | 8ft X 12ft riser | Rounds | should be reviewed at each event.
|  |  | Standing Lecturn + Mocrophone |  | DG or Conf. Chair may change
Seating for 90
Two 6ft tables at front of the room for door prizes or…
Speak-A-Thon | Room? | 06:15 PM thru 07:30 PM | 6ft table | Theatre
(could have Saturday afternoon) |  |  | Standing Lecturn
Chairs for 35
Friday night Speech Contest | Room? | 07:30 pm thru 08:30 pm | 8ft by 12ft riser | Rounds
(IF held) |  |  | Small table 3ft by 3ft
Standing Lecturn (Sound equipment provided by Toastmasters)
No Meal
8 ft table w 6 chairs for contestants - off to one side of the stage
Seating for 100
Water and glasses on contestant table
6ft table off to the side for sound equipment
Saturday |  | Time | Setup | Layout/Seating
Registration Area | Lobby | 07:00 AM thru 03:00 PM | Three 6ft tables, 4 chairs
Public Relations-Candidates Area | Lobby | 07:00 AM thru 08:00 PM | Two 8 ft tables
Opening Cerimonies | Room? | 08:00 am thru 09:15 am | Seating for 95 | Rounds or Theatre
|  |  | One 8ft table w 4 chairs on a riser | (works best if same
|  |  | Pitcher of water and glasses on front table | room used for lunch
|  |  | Standing lecturn & hotel microphone next to table | and dinner; and
|  |  | 6-7ft isle down center of room for parade of banners | possibly contest)
|  |  | Flag and stand | possibly contest)
6ft table off to the side of the head table for sound equipment
3 Education Sessions (3 rooms) | Room? | 09:30 am thru 12:00 pm | Each room: One 8ft table in front of the room | Theatre
Water in room
3 chairs in front
Seating for 40 people
Luncheon | Room? | 12:00 pm thru 01:30 pm | One head table for 10 on riser; second head table for 10 on floor | Rounds
Estimate of 100 attendees
Table lecture in center of head table
Meal tickets will be provided by Toastmasters and they will be color coded for meal options
One 8ft table w 4 chairs to the side of the head table
Standing lecturn next to table
6ft table off to the side of the head table for sound equipment
Business Meeting | Room? | 01:30 pm thru 03:00 pm | Two 8ft tables, 8 chairs at front of room | Theatre
One 8ft table 4 chairs off to the side in the front.
Seating for 90
International Speech Contest | Room? | 03:15 pm thru 04:30 pm | 8ft by 6ft riser | Rounds
(in Spring) |  |  | Small table 3ft by 3ft | Theatre
Standing Lecturn (Sound equipment provided by Toastmasters)
No Meal
8 ft table w 6 chairs for contestants - off to one side of the stage
Seating for 140
Water and glasses on table
6ft table off to the side of the head table for sound equipment
Education Session | Room? | 04:45 pm thru 05:30 pm | One 8ft table in front of the room | Theatre
|  | in Spring | Water in room
|  | 3:30 pm thru 4:30 pm | 3 chairs in front
in Fall
First Timers Reception | Room? | 05:30 pm thru 6:00 pm | Two 8ft tables and 2 or 3 round tables | Open
20 chairs
Banquet | Room? | 07:00 pm thru 10:00 pm | Two tier head table (Bottom tier on floor) for 10 people each | Rounds
Round tables to accommodate rest of 120 attendees
Table lecture and hotel microphone in center of head (top) table
Meal tickets will be provided by Toastmasters and they will be color coded for meal options
|  | Hall of Fame (after meal) | 8ft by 6ft riser (Minimum) - Opposite head table
|  | in Spring | 6ft table for awards next to head tables
A/V cart
Projector Screen
6ft table off to the side of the head table for sound equipment
Standing lecturn with microphone next to riser
|  | Humor Contest in Fall | See contest set up above

## Speech Contest
Role | Name | Notes | Phone | Email
LGET |  | In charge of entire contests
Contest Master |  | MC at contest
Chief Judge |  | Line up judges, counters, timers and brief
Contestants
Northern Division 1st
Eastern Division 1st
Central Division 1st
Southeast Division 1st
Metro Division 1st
Northern Division 2nd
Eastern Division 2nd
Central Division 2nd
Southeast Division 2nd
Metro Division 2nd
If a second contest
LGET |  | In charge of entire contests
Contest Master |  | MC at contest
Chief Judge |  | Line up judges, counters, timers and brief
Contestants
Northern Division 1st
Eastern Division 1st
Central Division 1st
Southeast Division 1st
Metro Division 1st
Northern Division 2nd
Eastern Division 2nd
Central Division 2nd
Southeast Division 2nd
Metro Division 2nd